## Sheet1
STAGE | ACTION | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
PRE-CAMPAIGN | Set-up of Google platforms as required (Google Ads, Google Analytics, Google Merchant Centre) | bar: Week 1 to Week 2
Detailed keyword / key term research to identify suitable keywords and search terms
Creation of target audiences
Upload of product catalogue to Google Merchant Centre | bar: Week 2 to Week 4
Implementation of required tracking codes | bar: Week 3 to Week 4
Testing | bar: Week 3 to Week 5
CREATIVE AND CONTENT | Agreeement of key messages
Agreement of content strategy
Planning of campaign product groups / brands / offers etc.
Development of required content / creatives | bar: Week 3 to Week 5
CAMPAIGN LIVE | Campaign Implementation | bar: Week 5
Ongoing monitoring and optimisation | bar: Week 5 to Week 12
Performance report set-up (including ROI calculation) | bar: Week 4 to Week 6
In-house training | bar: Week 5 to Week 12